|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| |  |  | | --- | --- | |  | project progress report | | | | |
| Project Name | Bus User Support System | Project Code | BUSS |
| Author | Nguyen Thanh Nam | Project Manager | Nguyen Thanh Nam |
| Date of Report | 19-06-2015 | Receiver | Supervisor |
| Reporting period[[1]](#footnote-1) | 27-05-2015 – 19-06-2015 | Nguyen Van Sang |

# Progress Description

|  |  |  |
| --- | --- | --- |
| Items | Information | Note |
| Start-date of project | 11-05-2015 |  |
| Estimated end-date | 28-08-2015 |  |
| Team size | 5 members | Nguyen Thanh Nam, Trinh Thi Tuyet Mai, Nguyen Le Tuan Cuong, Bui Bich Phuong, Tran Tu Anh |
| Total estimated effort | 350 person-days | 1 person-day = 8 person-hours |
| Total effort spent |  |  |
| Effort spent in this period | 100 person-days |  |
| Total effort left | 195 person-days |  |

# Customer Complaints

## None

# Customer Support

## None

# Change Management

## None

# Quality Activities

## None

# Tasks matches/missed

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task | Responsibility | Deliverable | Status | Remark | Re-schedule |
| Create Architecture Design | Nguyen Le Tuan Cuong | 07-06-2015 | Done |  |  |
| Create Screen Design | Nguyen Thanh Nam | 14-06-2015 | Done |  |  |
| Create Database Design | Trinh Thi Tuyet Mai | 16-06-2015 | Done |  |  |
| Create Class Design | Trinh Thi Tuyet Mai | 18-06-2015 | Done |  |  |
| Create Progress Report 2 | Trinh Thi Tuyet Mai  Nguyen Thanh Nam | 19-06-2015 | Done |  |  |
| Create Checklist Architecture Design | Trinh Thi Tuyet Mai | 07-06-2015 | Done |  |  |
| Create Checklist Screen Design | Trinh Thi Tuyet Mai | 07-06-2015 | Done |  |  |
| Create Checklist Database Design | Trinh Thi Tuyet Mai | 08-06-2015 | Done |  |  |
| Create Checklist Class Design | Trinh Thi Tuyet Mai | 08-06-2015 | Done |  |  |

# Tasks planned for next period

|  |  |  |  |
| --- | --- | --- | --- |
| Task | Responsibility | Deliverable | Planned end date |
| Create Progress Report 3 | Nguyen Thanh Nam  Trinh Thi Tuyet Mai | .docx | 14-07-2015 |
| Coding | Nguyen Thanh Nam  Trinh Thi Tuyet Mai | source code | 14-07-2015 |
| DB | Tran Tu ANh | source code | 14-07-2015 |
| Create Test Plan | Trinh Thi Tuyet Mai | .xls | 30-06-2015 |
| Create Test Case | Bui Bich Phuong | .xls | 14-07-2015 |

# Problems and Suggestions

***Author***

***Nguyen Thanh Nam***

1. [↑](#footnote-ref-1)